## Slide 1: Onboarding
Computational sciences, IT, and research informatics handover | October 2026

## Slide 2
Where you are landing
IT and infrastructure
Research informatics
Team and career growth
2026 results and 2027 planning
Cross-functional projects
3
4
8
10
14
18

## Slide 3: Where you are landing: a small team with board-visible stakes
6
computational team members today, including one new starter
What the function covers
Protein design pipeline and design-pipeline infrastructure
ML/AI modeling: binding prediction, active learning, ESM fine-tuning
Radiance (internal design and QC platform) and data infrastructure
Target ID, omics and bioinformatics analysis
Agentic AI: target assessment, literature, experiment design
IT coordination with Flagship IT and vendors, historically run by Diogo
Platform in one line: fully synthetic D-amino acid mini-binders against L-protein targets (Synteins). The computational team designs, scores and triages them; hit rate and assay quality are the metrics that move the business.
Why this role is wide: until now one person has acted as head of computation, de facto CAIO and IT owner. This deck separates those hats so you can decide which to keep.
Sources: Pandora vault (Abiologics Home, comp team digests 10/1 and 10/5), LT notes 10/1, Rob Albert email 10/7.

## Slide 4: IT and Infrastructure
Flagship IT, Baystate, OneVector and what is still open

## Slide 5: IT landscape: five vendors, one coordination gap
Party | Contact | What they do for Abiologics
Flagship IT (FSP IT) | Rob Albert; Dan Cochrane | Business partnership, POs and licenses; owns the storage gateway upgrade with Research Systems; biweekly Abio check-in
Baystate IT | Ben Farrow; Darrell Rhodes | Managed IT for the new site: VPN (live since Aug 31), endpoints, on-site engineer, network follow-ups
Technium | via Flagship IT | Built Abiologics VLANs at 99C and the site-to-site VPN into the AWS organization
Kyndryl, Tennex | via Flagship IT | Legacy and adjacent infrastructure vendors named in the catalog work; confirm scope and renewals
OneVector | Karen Scott, Amelia Sancilio, Gene Grella | Advisory and program-management support; Phase 1 closed Oct 13 (next slide)
The gap: no single owner reconciles these vendors against what the science needs. In July the idea was to use OneVector as a fractional CIO for exactly this. You are the natural owner; a software and service catalog now exists to work from.

## Slide 6: OneVector: Phase 1 is done, Phase 2 is your decision
33.5 / 40
SOW hours used by Oct 5; ended Oct 13
What Phase 1 delivered
Support for the 99 Coolidge move and post-move IT stabilization
Software and Service Catalog: systems, owners, contacts, renewals, costs, licensing
Catalog at "good place"; remaining gaps are ownership, Finance and FSP follow-ups, renewals
Phase 2 as OneVector proposes it
Finish renewal, cost, licensing and ownership data
Facilitate retire, consolidate or transition-to-Abio decisions on systems
Karen Scott has asked for times to scope it; reply is outstanding
Decision for you: continue, narrow or stop. Rob Albert asked what value was actually delivered, and Diogo asked OneVector for an hour-by-hour breakdown of Phase 1 plus a deliverables outline (answered at high level on Oct 5).
Context: Kala Subramanian is moving the MSA and SOW with a spend cap below $10K. If you take the IT owner role, Phase 2 may be unnecessary; if you do not, it is the cheapest owner you have.

## Slide 7: IT open items to pick up
Item | Owner / contact | Status and next step
Storage gateway cutover to private SGW | Joe Kennedy; Andrew Croneberger | New SGW is Entra-bound and live in the workload-1 AWS account; lab-device remount needs a downtime window. Biology confirmed ready Oct 13
Weights & Biases renewal | Andrew Croneberger | Renewal process unclear; raised Oct 6, no owner confirmed
OpenFold PO | Rob Albert | Renewal signed; PO still to be opened and paid
Sources: Joe Kennedy and Rob Albert emails (Jun to Oct 2026), OneVector IT touchpoint notes 9/29 and 10/6, comp team digest 10/5. Some items may have closed since.

## Slide 8: Research Informatics
Joe Kennedy and the Flagship research systems group

## Slide 9: Research informatics: what Joe Kennedy owns
Benchling and data model
Tenant admin, results schemas and data models
Benchling AI program: shared AI credits under Flagship central agreement; AI Day held Sep 15
Pulling Benchling data into S3 for analysis
Cloud and lab devices
AWS storage gateway and S3 environments
Lab device management (NinjaOne) and off-hours remounts
Software installs and licenses for scientists
Policy and vendors
ELN policy draft shared with Andrew in April
Vendor sessions, for example Seqera on site Oct 6
Sharepoint raw-data migration planning
Open threads: (1) pick a Benchling catch-up day for the team, an LT action from Oct 1; (2) data package consultants need to implement templates, still unclear; (3) team habit of reviewing Benchling entries weekly so they do not pile up; (4) SGW remount timing with Andrew.
Working style: Joe copies Diogo on most threads and acts on the lab and cloud side; the science-side owner is Andrew, with Jaclyn for lab scheduling. Set a standing monthly with Joe so informatics decisions are not made in email cc lines.
Sources: Joe Kennedy emails (Apr to Oct 2026), LT notes 10/1, comp team digests 10/1 and 10/5, FL111 and FL108 Benchling threads.

## Slide 10: Team and Career Growth
Who is on the team, what they are good at, where they are going

## Slide 11: Team makeup and skills
Person | Role | Core skills and current work | Notes
Andrew Croneberger | Software and infrastructure lead | Design pipeline and infra; storage gateway, Sentry and W&B; chasing the Adaptyv BLI gap | Top performer; single point of failure for infra
Nitya Talasila | Software engineer, Radiance owner | Radiance product and UI redo; data and infra; organizes comp huddles | Single point of failure for Radiance
Jeremy Amon | Computational protein designer | Rosetta interface-design experiment; tooling; solubility and designability insight; target-scan adviser | Steep ramp since joining about 9 months ago
Beth Kartchner | Computational protein designer (remote, Arizona) | Deep structure expertise; wet-lab triage; GFRAL benchmarking; ncAA notebook; MI6 Claude plug-in for target assessment | Recently promoted
Jiangchuan Ye | ML scientist (since Apr 27, 2026) | ESM fine-tuning, binding-prediction models, active learning; solubility follow-up | Sole ML scientist
Declan Evans | Computational protein designer (new) | Point person for target scan from a design perspective | Joined September 28
Sources: Talent Review prep 7/7, People notes, comp team digests 10/1 and 10/5, 1:1 notes.

## Slide 12: Talent snapshot from the July review (confidential)
Strengths to build on
Andrew: strongest delivery, trajectory toward head of software engineering in 2 to 3 years
Jeremy: high potential; principal-scientist track now, possible team lead later
Beth: built Claude plug-in for target assessment; structural biology expertise
Risks to manage
Andrew is the largest organizational single point of failure; no recovery path for infra
Nitya is the single point of failure for Radiance; with Andrew, infra is only two deep
Jiangchuan is the only ML scientist; the ML team structure is not yet planned
Two asks already made to the LT: (1) a mid-level engineer between Andrew and Nitya, which fixes both single points of failure and lets Andrew delegate; (2) put ML team structure on the 2027 roadmap. The job description for the engineer is still owed to Andrew.
Retention: all five rated low risk at mid-year. Keep it that way by delivering the career conversations on the next slide. Jeremy, Nitya and Jiangchuan had not stated aspirations; ask early.
Caveat: the review is five months old. Re-calibrate with your own read before using it.
Source: Talent Review prep 7/7 and LT Talent Discussion 7/7 (framework from Carolyn Pastore).

## Slide 13: Career growth: one concrete move per person
Person | Direction | Next move | Gating skill
Andrew | Lead software engineering | Formalize his team: Nitya solid-line plus a mid-level hire | Delegation and time-boxing deep dives
Jeremy | Principal scientist; later team lead | Adviser role on target scan; trial of direct-report range | Tell us: technical authority or leading people
Beth | More responsibility, strategic scope | Own the agentic target assessment end to end, at scale. Expand understanding of the business | Options before constraints; company-level "why". Title just changed, so this year is demonstrating readiness
Nitya | Deeper technical IC under Andrew | Radiance UI redo as a stretch into new tech | Proactive, forward-looking ownership
Jiangchuan | Scientist track, too early to call | Narrow to two owned priorities | Focus; initiative as he settles
Declan | To be set | Target scan from a design lens | Define in first 30 days
Sources: Talent Review prep 7/7; target-scan plan from LT 10/1. Personal circumstances intentionally left out of this record.

## Slide 14: 2026 Results and 2027 Planning
What we built, what the board now expects

## Slide 15: 2026 in review: from point solutions to a platform
Platform and pipeline
Design pipeline review and co-folding strategy (Jun)
Radiance platform with new QC features
Rosetta interface-design experiment under way
AI and agentic
TARDIS six-agent target assessment
GFRAL active-learning proof of concept on 2,044 sequences
Team-wide Claude adoption session (Oct 1)
Team and operations
ML and protein-design hiring: two roles, 20+ candidates screened
Two hires landed (Apr, Sep/Oct)
Most actionable finding: a bug in the computational feature pipeline moved the correlation by 0.50 in the GFRAL analysis. Validate pipeline outputs before trusting model gains.
Still open: GFRAL benchmarking data (CD, crude LC-MS) final analyses; our BLI controls bind weaker than Adaptyv's on the same sequence (about $2 to 3K per plate to chase);
Sources: TARDIS and agentic summaries, comp team digests 10/1 and 10/5, 6/24 pipeline review, LT notes 10/1. Chiara asked each lead for a 2026 retro slide for the 2027 workshop.

## Slide 16: 2027 plan: build on 2026 growth (proposed, to validate with LT)
Workstream | 2026 baseline | 2027 goal | Needs
Target scan and new programs | v0 scan by Diogo; Declan on point, Jeremy advising | Read before year end; target list ready for BD; programs start in Jan | Clear design-feasibility score; Chiara mandate
Hit finding and assay quality | Benchmarks (GFRAL, IL7RA); BLI gap vs Adaptyv | Higher hit rate per cycle; closed BLI discrepancy | Adaptyv green light; plate budget
Platform: Radiance and infra | Infra concentrated in Andrew | Two-deep infra; UI redo planned and delivered | Mid-level engineer hire
ML and agentic AI | One ML scientist; TARDIS/MI-6 and agents in production use | ML team structure; API migration of agents | ML headcount case; compute budget
Data and IT | Benchling, SGW cutover, catalog 1.0 | Single IT owner; renewals rationalized | OneVector decision

## Slide 17: 2027 risks and what to decide first
Risks
Feasibility: Jeremy raised concerns at the Oct 7 townhall that two DCs a year is a stretch
Team pushback: twice the team resisted at-scale testing and 2 DCs a year
Concentration: infra and Radiance single points of failure
Decide in first 30 days
What counts as a workable target for Abiologics from a design perspective
Headcount: mid-level engineer first, ML structure second
OneVector Phase 2 and who owns IT
Calendar: 2027 workshop prep is live; each LT member owes a 2026 rear-view and a 2027 front-load deck. The target-scan read is due before year end. New programs begin in Q1.
Sources: Townhall 10/7, Jeremy 1:1 10/7, LT 10/1 and 10/8, Chiara email 10/8.

## Slide 18: Cross-Functional Projects
Led by the computational team

## Slide 19: Target ID and target scan: the most strategic project
How it got here
Oct 2025: first target-ID script pulled disease targets from Open Targets, then added GTEx, HPA, TTD and ChEMBL to list membrane proteins our Synteins could address
Jun 2026: TARDIS prioritized Matriptase, KIM-1 and 5T4 for deeper work
Sep 30: large-scale target scan (target_scan) walked through with Chiara
Where it goes
LT 10/1 made it a board-visible priority
Declan Evans on point; Jeremy Amon advising
Output: read before year end and a back-pocket target list for BD
Open: score targets intelligently from a quick structural analysis in the L form
Why it matters: the company needs to move from one-target-at-a-time work to scanning the proteome for what design can reach. Diogo treats it as existential.
Sources: Target ID for Abiologics 10/7/2025, TARDIS 6/16, Chiara 1:1 9/30, LT 10/1, comp team digest 10/5.

## Slide 20: Kidney expression analysis with Chiara
Method (KPMP plus GTEx)
Pan-tissue healthy reference from GTEx single-cell plus healthy kidney from KPMP
Specificity by cell type using donor-level pseudobulk and a tau metric
Map KPMP CKD and AKI cells into the frozen healthy reference
What Chiara asked for
Podocyte targeting is the next focus: surface proteins mostly expressed in podocytes and not in the literature
Address must persist in disease (KPMP) and stay specific vs other tissues (GTEx, HPA)
Safety lens on SEMA3A, TROP2, FOLR1; PAPPA biodistribution
Status: analysis designs, KPMP data acquisition and README for Chiara are done (Oct to Nov 2025); podocyte request dates Jan 9, 2026. Final candidate lists and current status were not found in the notes. Ask Chiara.
Reusable asset: the same specificity workflow can feed target scan for any tissue.
Sources: KPMP address analysis 10/28/2025, KPMP + GTEx 10/29/2025, Chiara 1:1s 10/23/2025, 12/11/2025, 1/9/2026.

## Slide 21: Bioinformatics and data work: spread across programs
Stream | What the team does | Customers
Omics and disease-area diligence | Single-cell and bulk expression analysis, disease-area strategy (FAP, ADPKD, GLP-1) | Chiara; LT
Oncology data (FAP) | Biodistribution and tumor-uptake data support; weekly Onc Data meeting | Brad Kubick; Martin Tremblay
G Project (GFRAL) | Developability and scoring input; benchmarking data; active learning | Kevin Lai
Data model and Benchling | Results schemas, Benchling to S3, data package requirements for consultants | Andrew; Comp team
Pipeline tooling | Rosetta, PyMol, ncAA notebook work, property prediction models | Design team; Beth and Nitya
Sources: Disease area strategy 11/24/2025, Onc Data and G Project meetings (9/25 to 10/9), comp team digests. Customer column inferred from invites.

## Slide 22: Agentic AI and literature mining
What exists
LiteratureAgent for literature mining PoC
ExperimentDesignAgent PoC
TARDIS: six-agent target assessment with a GO/NO-GO call; reports built for GFRAL, FOLR1, RANKL, SOST, Kv1.3, IAPP and PAPPA
MI6 Claude plug-in for target assessment (Beth, shown at LT 9/24)
Next steps
Beth to own the agentic target end to end
Avoid "tool monoculture": agents converge on the same scoring proxies
Consolidate agentic AI across multiple cases at Abiologics
Sources: Abio agentic AI summary, LT 9/24, TARDIS 6/16, Computational operating model proposal (email 8/19/2025), Robot uprising session 10/1.